## WP6_IO
			WP6 :	Work Package 6: Dissemination, Exploitation and Standardization	WP6 Leader: TWT GmbH
			Inputs
			Reference(*)	Description	From / (MS Project predecessor)
					WP	Task
Input for Task No.?	MS Project Identifier	This Input is part of Deliverable	Input Reference (*)	Description of Input	Producer WP	Producer Task	Comes from what Task? MS-Project Identifier	Preliminary Deadline (latest!)	Status (not started/ in progress/ done)

			Ouputs
			Reference(*)	Description	To / (MS Project successor)
					WP	Task
Output from Task No.?	MS Project Identifier	Task Output is part of Deliverable	Output Reference (*)	Description of Output	User WP	User Task	Needed by what Task for MS-Project Identifier	Preliminary delivery time	Status (not started/ in progress/ done)

			(*) :	[I;O] index_WP number_T[ask] number
			Examples :	I1_WP2_T2_1 = Input 1 mandatory for the Task 2 of the WP2
				O2_WP3_T1_2 = Output 2 resulting from Task 1 of WP3

				**): MS Project Task Idenifier:WP: n, Task: m, Output: p, converts into Tn.m.o.p; Example for MS Project Task Output Identifier: WP: 2, Task: 4, Output: 1, converts into 2.4.1 (could also be understood as Output of [Sub-]Task: T2.4.1)

## New Template
			WPx :	Work Package x: xxxxxxxxx	WP1 Leader: xxxx
			Inputs
			Reference(*)	Description	From / (MS Project predecessor)
					WP	Task
Input for Task No.?	MS Project Identifier	This Input is part of Deliverable	Input Reference (*)	Description of Input	Producer WP	Producer Task	Comes from what Task? MS-Project Identifier	Preliminary Deadline (latest!)	Status (not started/ in progress/ done)

			Ouputs
			Reference(*)	Description	To / (MS Project successor)
					WP	Task
Output from Task No.?	MS Project Identifier	Task Output is part of Deliverable	Output Reference (*)	Description of Output	User WP	User Task	Needed by what Task for MS-Project Identifier	Preliminary delivery time	Status (not started/ in progress/ done)

			(*) :	[I;O] index_WP number_T[ask] number
			Examples :	I1_WP2_T2_1 = Input 1 mandatory for the Task 2 of the WP2		PA: Public Authority
				O2_WP3_T1_2 = Output 2 resulting from Task 1 of WP3

				**): MS Project Task Idenifier:WP: n, Task: m, Output: p, converts into Tn.m.o.p; Example for MS Project Task Output Identifier: WP: 2, Task: 4, Output: 1, converts into 2.4.1 (could also be understood as Output of [Sub-]Task: T2.4.1)

			(*) :	[I;O] index_WP number_T[ask] number	new format
			Examples :	I1_WP2_T2_1 = Input 1 mandatory for the Task 2 of the WP2	n/a
				O2_WP3_T1_2 = Output 2 resulting from Task 1 of WP3	T3.1.2

				In order to keep things simpel, each Task can have only one output, but may need one or more inputs. (that makes it easy to trace potential delays, if a task has several outputs, then potential delays are almost impossible to trace.
				If we keep it that simple, then we can call the output of the task identical wit the Task itself!
				Inputs can either come from the outsite world or from one earlier task from within the project. That input can then be called identical with the particular input from that earlier task.
				Please keep these simple principles in mind.

## old Template
a	WP Title
Inputs
Reference(*)	Description	From / (MS Project predecessor)
		WP	Task

Ouputs
Reference(*)	Description	To / (MS Project successor)
		WP	Task

(*) :	[I;O] index_WP number_T[ask] number
Examples :	I1_WP2_T2_1 = Input 1 mandatory for the Task 2 of the WP2
	O2_WP3_T1_2 = Output 2 resulting from Task 1 of WP3

## WP1_IO
			WP1 :	Work Package 1: Project Management,	WP1 Leader: DB Netz
			Inputs
			Reference(*)	Description	From / (MS Project predecessor)
					WP	Task
Input for Task No.?	MS Project Identifier	This Input is part of Deliverable	Input Reference (*)	Description of Input	Producer WP	Producer Task	Comes from what Task? MS-Project Identifier	Preliminary Deadline (latest!)	Status (not started/ in progress/ done)

			Ouputs
			Reference(*)	Description	To / (MS Project successor)
					WP	Task
Output from Task No.?	MS Project Identifier	Task Output is part of Deliverable	Output Reference (*)	Description of Output	User WP	User Task	Needed by what Task for MS-Project Identifier	Preliminary delivery time	Status (not started/ in progress/ done)
FPP v2.2 + funding reports	1.1.1	D1.1.1	O1_WP1_T1_1	Project Plan (Schedule)	WP*			31.03.2013	in progress
	1.1.2	D1.1.1	O2_WP1_T1_1	Project Plan (Organisation)	WP*			31.03.2013	in progress
	1.1.3	D1.3.1	O3_WP1_T1_1	Project Guide on Quality Assurance	WP4+2			31.03.2013	in progress
	1.1.1	D1.2.1	O1_WP1_T2_4	Periodic Project Report(s)	WP1	ITEA2, PA		31.01.2013	in progress
	1.1.0	D1.2.2	O1_WP1_T2_3	Periodic Project Report(s)	WP2	ITEA2, PA		31.07.2013	no started
	1.1.1	D1.2.3	O1_WP1_T2_2	Periodic Project Report(s)	WP3	ITEA2, PA		31.01.2014	no started
	1.1.2	D1.2.4	O1_WP1_T2_1	Periodic Project Report(s)	WP4	ITEA2, PA		31.07.2014	no started
	1.1.3	D1.2.5	O1_WP1_T2_0	Periodic Project Report(s)	WP5	ITEA2, PA		31.01.2015	no started
	1.1.5	D1.1.2	O2_WP1_T2_1	Final Report	WP6	ITEA2, PA		30.06.2015	no started
FPP	1.1.6		O1_WP1_T1_2	Provide Initial Backlog Structure (xls)	WP*			31.03.2013	in progress
	1.1.7	D1.1.2	O2_WP1_T1_2	Provide Final Backlog Structure	WP*			31.07.2013	no started
Eclipse openETCS OLT	1.1.8	D1.4.1	O1_WP1_T3_1	IPR Plan	WP2+4			28.02.2013	in progress
Eclipse	1.1.9	D1.3.1	O4_WP1_T1_1	Development Guideline?	WP*			31.01.2013	in progress
Legal Expert Meetings	1.1.10	D1.1.2.new	O4_WP1_T1_2	PCA V.1.0 (Project Cooperation Agreement) Preparation and finalization of the German consortium agreement, defining an initial governance concept				31.12.2012	done
Legal Expert Meetings	1.1.11	D1.1.3.new	O4_WP1_T2_2	PCA V.2.0 (Project Cooperation Agreement) Preparation and finalization of the international consortium agreement, defining an initial governance concept				31.03.2013	in progress
	1.1.12		O4_WP1_T1_3	Progress monitoring and tracking to identify deviations from the work plan and leverage counter measures
	1.1.13		O4_WP1_T1_4	Identifying obstacles during the process and remove them
	1.1.14		O4_WP1_T1_5	Resource allocation monitoring to ensure that the projects stays within the allocated budget
	1.1.15		O4_WP1_T1_7	Setting up a project management structure by arranging meetings with the project Management board and individual Work package leaders and national coordinators				31.03.2013	in progress
	1.1.16		O4_WP1_T1_8	Perform project reporting according to time plan
	1.1.17		O4_WP1_T1_9	Establish guidelines as part of the governance for quality assurance and perform quality tracking				31.03.2013	in progress
WP reports	1.1.18		O4_WP1_T1_10	Manage communication to the outside world and maintaining information exchange with relevant stakeholders
outsite world	1.1.19		O4_WP1_T1_11	Implementing and maintaining an advisory board and facilitate regular meetings				26.02.2012	done
FPP v2.2 + funding reports	1.1.20		O4_WP1_T1_12	FPP update and CR to ITEA2				31.03.2013	in progress
state-of-the-art report	1.1.21		O4_WP1_T1_13	Set-up and provide training opportunities for new technologie or skills needed in the project				31.03.2013	in progress

			(*) :	[I;O] index_WP number_T[ask] number
			Examples :	I1_WP2_T2_1 = Input 1 mandatory for the Task 2 of the WP2		PA: Public Authority
				O2_WP3_T1_2 = Output 2 resulting from Task 1 of WP3

				**): MS Project Task Idenifier:WP: n, Task: m, Output: p, converts into Tn.m.o.p; Example for MS Project Task Output Identifier: WP: 2, Task: 4, Output: 1, converts into 2.4.1 (could also be understood as Output of [Sub-]Task: T2.4.1)

## WP2_IO
			WP6 :	Work Package 6: Dissemination, Exploitation and Standardization	WP6 Leader: TWT GmbH
			Inputs
			Reference(*)	Description	From / (MS Project predecessor)
					WP	Task
Input for Task No.?	MS Project Identifier	This Input is part of Deliverable	Input Reference (*)	Description of Input	Producer WP	Producer Task	Comes from what Task? MS-Project Identifier	Preliminary Deadline (latest!)	Status (not started/ in progress/ done)
2.2.2			I1_WP2_T2_2	Report of existing methodologies in signaling or similar industrial contexts (State-of-the-art)	WP2		2.2.1
2.2.2			I2_WP2_T2_2	Set of requirements to be fulfilled according to CENELEC standards (state-of-the-art)	WP2		2.2.1
2.2.3			I1_WP2_T2_3	Definition of the overall process for the formal description of ETCS and the rail system it works in	WP2		2.2.2
2.2.3			I2_WP2_T2_3	Definition of the methods used to perform the formal description	WP2		2.2.2
2.2.3			I3_WP2_T2_3	Results of the previous methods being applied to ETCS	WP2		2.2.2
				Quality Plan	WP1		1.?.?
				CENELEC and other Standards	ERA/UNISIG
				Operational rules	DB, SNCF,
				Interview with stake holders	varios
				UNISIG Subsets 026, 91, 88, 76, (list of mandatory subsets)	ERA/UNISIG
				Track UC2 (NL IM: ProRail,) UC3 (DB Netz);	ProRail, DB Netz
				Track side scenarios ?	ERA?, ÖBB
				List of Stakeholder	WP1
			4.1a	D4.1a: preliminaryEvaluation criteria on V&V	WP 4				in progress 31.03.2013
			4.4a	D 4.4a preliminary Evaluation criteria on safety	WP 4				in progress 31.03.2013

			Ouputs
			Reference(*)	Description	To / (MS Project successor)
					WP	Task
Output from Task No.?	MS Project Identifier	Task Output is part of Deliverable	Output Reference (*)	Description of Output	User WP	User Task	Needed by what Task for MS-Project Identifier	Preliminary delivery time	Status (not started/ in progress/ done)
	2.2.1.1	D2.1	O1_WP2_T2_1	D2.1: Report on existing methodologies / Report of existing methodologies in signaling or similar industrial contexts (State-of-the-art)	WP2	T2_2/T 7.1 /T7.2		15.01.2013	un progress /15.03.2013

	2.2.1.2	D2.2	O2_WP2_T2_1	D2.2: Set of requirements to be fulfilled according to CENELEC standards (state-of-the-art)	WP4	T 7.1 T7.2T		15.01.2013	in progress 15.03.2013
	2.2.2.1	D2.3	O1_WP2_T2_2	D2.3: Definition of the overall process for the formal description of ETCS and the rail system it works in / Description of the OpenETCS project : activities and case study (overall design plan) / - description of the process to be applied in the OpenETCS : / - design and development par of the process / - usual safety activities of such kind of process : this activity is not a part of the project / - description of the system study in the OpenETCS project and its environment / - high level description of the subset + link to reference documentation (subset 26) / - high level description of the environement of the system and main function / - reference document subset 091 to the list of safety properties	WP 4/ WP 7
		D 2.3a	O1_WP2_T2_2	D 2.3a: preliminary Definition of the overall process for the formal description of ETCS and the rail system it works in	WP 4/ WP 7				28.02.2013
		D 2.3b	O1_WP2_T2_2	D 2.3b: intermediate Definition of the overall process for the formal description of ETCS and the rail system it works in	WP 4/ WP 7				in progress 15.03.2013
		D 2.3c	O1_WP2_T2_2	D 2.3c: Final Definition of the overall process for the formal description of ETCS and the rail system it works in	WP 4/ WP 7				in progress 31.05.2013
	2.2.2.2	D2.4	O2_WP2_T2_2	D2.4: Definition of the methods used to perform the formal description / Detailed process in regards of state of the art results and Cenelec standard requirements (detailed design plan) / - For each step of the process defined in T.2.2.1 : / - objectives of the step / - Input/output / - proposed techniques / - rules on languages and tools	WP 4/ WP 7
		D 2.4a	O2_WP2_T2_2	D 2.4a: preliminary Definition of the methods used to perform the formal description	WP 4/ WP 7				28.02.2013
		D 2.4b	O2_WP2_T2_2	D 2.4b: intermediate Definition of the methods used to perform the formal description	WP 4/ WP 7				in progress 31.03.2013
		D 2.4c	O2_WP2_T2_2	D 2.4c: Final Definition of the methods used to perform the formal description	WP 4/ WP 7				in progress 31.05.2013
	2.2.2.3	D2.5	O3_WP2_T2_2	D2.5: Methods and tools benchmarking methodology / (change of title from D2.5) / - Case studies for the benchmark / - Safety properties for the benchmark / - process of the benchmark	WP 4/ WP 7
		D 2.5a	O3_WP2_T2_2	D 2.5a: preliminary Methods and tools benchmarking methodology	WP 4/ WP 7				28.02.2013
		D 2.5b	O3_WP2_T2_2	D 2.5b: intermediate DMethods and tools benchmarking methodology	WP 4/ WP 7				in progress 31.03.2013
		D 2.5c	O3_WP2_T2_2	D 2.5c: Final Methods and tools benchmarking methodology	WP 4/ WP 7				in progress 31.05.2013
	2.2.3.1	D2.6	O1_WP2_T2_3	D2.6: Set of requirements for the model used and the modeling process: / These requirements describe the language and the formalism that will be used for the modeling of the ETCS OBU subset. It also contains requirement on the modeling methodology, and describe the part of the ETCS OBU that will be modelled.	WP 3, WP 4, WP 7
		D 2.6a	O1_WP2_T2_3	D 2.6a: preliminary Set of requirements for the model used and the modeling process:	WP 3, WP 4, WP 7				15.01.2013
		D 2.6b	O1_WP2_T2_3	D 2.6b: intermediate Set of requirements for the model used and the modeling process:	WP 3, WP 4, WP 7				in progress 31.03.2013
		D 2.6c	O1_WP2_T2_3	D 2.6c Final Set of requirements for the model used and the modeling process:	WP 3, WP 4, WP 7				in progress 31.05.2013
	2.2.3.2	D2.7	O2_WP2_T2_3	D2.7: Set of requirements for API: / These requirements describe the API and Runtime model that will allow to provide an abstract layer allowing the model to be high-level. In particular it will provide an abstract view of the hardware and I/O.	WP3, WP4, WP7
		D 2.7a	O2_WP2_T2_3	D 2.7a: preliminary Set of requirements for API:	WP3, WP4, WP7				15.01.2013
		D 2.7b	O2_WP2_T2_3	D 2.7b: intermediate Set of requirements for API:	WP3, WP4, WP7				in progress 15.03.2013
		D 2.7c	O2_WP2_T2_3	D 2.7c Final Set of requirements for API:	WP3, WP4, WP7				in progress 31.05.2013
	2.2.3.3	D2.8	O3_WP2_T2_3	D2.8: Set of requirements for the tools used: / These requirements describe the tool chain that will be use for the development of the OpenETCS model and software.	WP3, WP4, WP 5, WP 7
		D 2.8a	O3_WP2_T2_3	D 2.8a: preliminary Set of requirements for the tools used:	WP3, WP4, WP 5, WP 7				15.01.2013
		D 2.8b	O3_WP2_T2_3	D 2.8b: intermediate Set of requirements for the tools used:	WP3, WP4, WP 5, WP 7				in progress 15.03.2013
		D 2.8c	O3_WP2_T2_3	D 2.8c final Set of requirements for the tools used:	WP3, WP4, WP 5, WP 7				in progress 31.05.2013
	2.2.3.4	D2.9	O4_WP2_T2_3	D2.9: Set of requirements for the verification and validation process: / These requirements describe the verification and validation process, including safety activities (safety analyses).	WP4, WP7
		D 2.9a	O4_WP2_T2_3	D 2.9a: preliminary Set of requirements for the tools used:	WP4, WP7				15.01.2013	WP 4 will set up a first preliminary version at the end of 03.2013
		D 2.9b	O4_WP2_T2_3	D 2.9b: intermediate Set of requirements for the tools used:	WP4, WP7				in progress 15.03.2013
		D 2.9c	O4_WP2_T2_3	D 2.9c final Set of requirements for the tools used:	WP4, WP7				in progress 31.05.2013

				**): MS Project Task Idenifier:WP: n, Task: m, Output: p, converts into Tn.m.o.p; Example for MS Project Task Output Identifier: WP: 2, Task: 4, Output: 1, converts into 2.4.1 (could also be understood as Output of [Sub-]Task: T2.4.1)

## WP7_IO
			WP7:	Work Package 7: openETCS Tool chain,	WP7 Leader: Formal Mind
			Inputs
			Reference(*)	Description	From / (MS Project predecessor)
					WP	Task
Input for Task No.?	MS Project Identifier	This Input is part of Deliverable	Input Reference (*)	Description of Input	Producer WP	Producer Task	Comes from what Task? MS-Project Identifier	Preliminary Deadline (latest!)	Status (not started/ in progress/ done)
		D 2.1	T7.1 / T7.2	WP2: List of suitable means of description (state-of-the-art, tools, methods, suitable modelling languages, formal, requirements )	2	1	2.1
		D 2.5	T7.1 / T7.2	WP2: Small representative subset of ERTMS requirements in order to evaluate tools/languages	2	T2.3.	2.2.3			D2.5: Methods and tools benchmarking methodology
		D 2.6 - D 2.9	T7.1 / T7.2	WP2: Preliminary requirements	2	3	2.3			D2.2, D2.6, D2.7, D2.8, D2.9
		D 2.6 - D 2.9	T7.1 / T7.2	WP2: Requirements	2	3	2.3			D2.2, D2.6, D2.7, D2.8, D2.9
		D 2.1	T7.1	WP2: List of suitable tools (based on State of the Art Analysis)	2	1	2.1
			T7.1	List of target platforms, based on the tools being evaluated (1.2)	7	1
		D 2.3		WP2:Requirements of process	2	2	2.2			WP1 QA-Plan
		D 2.4	T7.2	WP2: Definition of method	2	2	2.2			D2.4
			T7.2	Decision of the final choice for the core language	7	1
			T7.2	WP3b formalized API	3	7	3.7
		D 4.1	T7.2	Those sufficient elements of WP4 V&V Plan to evaluate tools	4		4.?			D4.1
		D 4.5	T7.2	Those sufficient elements of WP4 Safety case to evaluate tools	4		4.?			D4.4
			T7.3	I:O7.1.1: Formal Model representing the sample spec, one for each candidate	7	1
			T7.3	I:O7.1.2 Documentation of the changes to each means of description used (if any)	7	1
			T7.3	I:O7.1.4 Decision on the final means of description / choice(s)	7	1
			T7.3	I:O7.1.3: Evaluation of the models against the WP2 requirements	7	1
			T7.3	I:O7.1.8 Decision on the final tool choice(s)	7	1
			T7.3	I:O7.1.11: Selection of Tool Platform	7	1
			T7.3	I:O7.2.6: Verification and test tool choice(s)	7	2
		D 2.3, D 2.4	T7.3	WP2: Definition of method / process	2	2	2.2
			T7.3	I:O7.2.5: Captured and organised designer / requirements	7	2				continues
			T7.3	WP1-7: Feedback from project partners (All WPS)	1		1.?			continues
			T7.3	I:O7.1.8 Decision on the final tool choice(s)	7	1				continues
			T7.3	I:O7.1.11: Selection of Tool Platform	7	1				continues
			T7.3	I:O7.3.4: Infrastructure evolution strategy	7	3				continues
			T7.3	WP1-7: Bugs report and feedback from project partners (All WPS)	1-7					continues
			T7.3	I:O7.3.1 Tool chain development plan (or equivalent)	7	3				continues
			T7.3	I:O7.3.2 Specification of tool interoperability mechanisms	7	3				continues
			T7.3	I:O7.3.4: Infrastructure evolution strategy	7	3				continues
			T7.3	I:O7.3.6 Tool chain qualification test suite	7	3				continues
			T7.4	WP1: Requirements for the open source ecosystem	1-7					continues
			T7.4	WP1: IPR policy	1

			Ouputs
			Reference(*)	Description	To / (MS Project successor)
					WP	Task
Output from Task No.?	MS Project Identifier	Task Output is part of Deliverable	Output Reference (*)	Description of Output	User WP	User Task	Needed by what Task for MS-Project Identifier	Preliminary delivery time	Status (not started/ in progress/ done)
	7.1.1		O7.1.1	Formal Model representing the sample spec, one for each candidate	7	1
	7.1.2		O7.1.2	Documentation of the changes to each means of description used (if any)	7	1
	71.3		O71.3	Evaluation of the models against the WP2 requirements	7	1
	7.1.4		O7.1.4	Decision on the final means of description choice(s)	7	1
	7.1.5		O7.1.5	Evaluation of tool and model for each prototype	7	1
	7.1.6		O7.1.6	Documentation of the changes to each tool (if any)	7	1
	7.1.7		O7.1.7	Evaluation of the tools against the WP2 requirements	7	1
	7.1.8		O7.1.8	Decision on the final tool choice(s)	7	1
	D7.1		D7.1	Report on the final choice(s) for the primary tool chain (means of description, tool and platform)	7	3			31.07.2013
	7.1.9		O7.1.9	Evaluation of each tool platform against WP2 requirements, independent of target tool	7	2
	7.1.10		O7.1.10	Evaluation of tool platform in the context of specific target tools	7	2
	7.1.11		O7.1.11	Selection of Tool Platform (and reasoning)	7	2
	7.2.1		O7.2.1	Evaluation of supporting tools and methods against the WP2 requirements and task 1 choices	7	2
	7.2.2		O7.2.2	Decision on the supporting tools choice(s)	7	2
	D7.2		D7.2	Report on all aspects of secondary tooling (results of T7.2)	7	3			Must be defined
	7.2.3		O7.2.3	Model Transformation Strategy	7	3
	7.2.4		O7.2.4	Code Generation Strategy	7	3
	7.2.5		O7.2.5	Captured and organized designer requirements	7	3
	7.2.6		O7.2.6	V&V tool choice	7	3
	7.2.7		O7.2.7	Test automation tool choice with experience report	7	3
	7.2.8		O7.2.8	Safety analyses tools choices	7	3
	7.3.1		O7.3.1	Tool chain development plan (or equivalent)	7	3				WP1 QA-Plan
	7.3.2		O7.3.2	Specification of tool interoperability mechanisms	7	3
	7.3.3		O7.3.3	Guideline for the tool chain according to CENELEC	7	3
	7.3.3		O7.3.3	Specification of primary and support tool chain architecture and its embedding into the platform	7	3
	7.3.4		O7.3.4	Infrastructure evolution strategy	7	3
	7.3.5		O7.3.5	Tool chain infrastructure maintenance	7	3
	7.3.6		O7.3.6	Tool chain qualification test suite	4	?
	7.3.7		O7.3.7	Tool chain maintenance and debug & continuously	3	8
		D7.3		Tool Chain Qualification Process Description	4	?			Must be defined
	7.3.8		O7.3.8	Tool chain releases & follow the scrum	3	8
	7.3.8.1		O7.3.8.1	Preliminary Secondary Tools Platform - Prototype
	7.3.8.2		O7.3.8.2	Final Secondary Tools Platform - Prototype
		D7.4		Tool chain first release	3	8			01.12.2013
	7.4.1		O7.4.1	Initial proposal for license model	1-7
	7.4.2		O7.4.2	Initial proposal for open source development process	1-7
	7.4.3		O7.4.3	Initial proposal for infrastructure and tools	1-7
	7.4.4		O7.4.4	Adaptation of license model	1-7
	7.4.5		O7.4.5	Adaptation of open source development process	1-7
	7.4.6		O7.4.6	Adaptation of infrastructure and tools	1-7
		D7.5		Ecosystem Artefacts	1-7				Must be defined
				Documentation of the ecosystem and evaluation of technical risk concerning safety and security inside the ecosystem	WP1?	QA-Plan

			(*) :	[I;O] index_WP number_T[ask] number
			Examples :	I1_WP2_T2_1 = Input 1 mandatory for the Task 2 of the WP2
				O2_WP3_T1_2 = Output 2 resulting from Task 1 of WP3

				**): MS Project Task Idenifier:WP: n, Task: m, Output: p, converts into Tn.m.o.p; Example for MS Project Task Output Identifier: WP: 2, Task: 4, Output: 1, converts into 2.4.1 (could also be understood as Output of [Sub-]Task: T2.4.1)

## WP3_IO
			WP3 :	Work Package 3: Modelling – Code Generation	WP3 Leader: Alstom
			Inputs
			Reference(*)	Description	From / (MS Project predecessor)
					WP	Task
Input for Task No.?	MS Project Identifier	This Input is part of Deliverable	Input Reference (*)	Description of Input	Producer WP	Producer Task	Comes from what Task? MS-Project Identifier	Preliminary Deadline (latest!)	Status (not started/ in progress/ done)
		D 2.6	I1_WP3_T1	Set of modelling requirements	WP2	T3	2.2.3.1		not started		O1_WP2_T2_3
		D 7.4, extra input D 7.1	I2_WP3_T1	Primary Tool Platform - Prototype	WP7	T3	7.3.8		not started	D7.4	O7.3.8
		D 2.7	I1_WP3_T2	Set of API requirements	WP2	T3	2.2.3.2		not started		O2_WP2_T2_3
		D 2.9	I2_WP3_T2	Set of safety requirements	WP2	T3	2.2.1.2		not started		O2_WP2_T2_1
		will be discussed by WP leader of 7 and 3	I1_WP3_T3	Secondary Tools Platform - Prototype	WP7	T4	7.3.8.1		not started		O7.3.8.1
		will be discussed by WP leader of 7 and 3	I3_WP3_T1	Primary Tool Platform - Final	WP7	T3			not started		???
		will be discussed by WP leader of 7 and 3	I2_WP3_T3	Secondary Tools Platform - Final	WP7	T4			not started		???
		D 2.4	will be defined??	Set of requirements for the process	WP2	T2.2			in progress

			Ouputs
			Reference(*)	Description	To / (MS Project successor)
					WP	Task
Output from Task No.?	MS Project Identifier	Task Output is part of Deliverable	Output Reference (*)	Description of Output	User WP	User Task	Needed by what Task for MS-Project Identifier	Preliminary delivery time	Status (not started/ in progress/ done)
	3.2.1		O1_WP3_T2	Functional Model - Protype	WP4	T2 (?)	4.2.	31.08.2013 will be discussed by WP3?	not started
	3.2.2		O2_WP3_T2	Functional API - Prototype	WP4	T2(?)	4.2.	31.08.2013 will be discussed by WP3?	not started
	3.3.1		O1_WP3_T3	System Architecture Model - Prototype	WP4	T3 (?)	4.3.	Will be discusse by WP 3 and 4?	not started
	3.3.2		O2_WP3_T3	System API - Prototype	WP5	T1 (?)	5.1.?		not started
	1.3.4		O1_WP3_T4	PiEM - Prototype	WP5	T1 (?)	5.1., 4.3	Will be discusse by WP 3 and 4?	not started
	3.2.3		O3_WP3_T2	Functional Model - Final	WP4	T2 (?)	4.2.	31.07.2014	not started
	3.2.4		O4_WP3_T2	Functional API - Final	WP4	T2(?)	4.2.	31.07.2014	not started
	3.2.4.a		O4_WP3_T2	Primineraly Functional API - Final	WP4	T2(?)	4.2.	30.04.2013	not started
	3.3.3		O3_WP3_T3	System Architecture Model - Final	WP4	T3 (?)	4.3.	T0+32	not started
	3.3.4		O4_WP3_T3	System API - Final	WP5	T1 (?)	5.1., 4.3	T0+32	not started
	3.4.2		O2_WP3_T4	PiEM - Final	WP5	T1 (?)	5.1.?	Will be discusse by WP 3 and 4?	not started
				Protype			?.?	Will be discusse by WP 3 and 4?	not started

			(*) :	[I;O] index_WP number_T[ask] number
			Examples :	I1_WP2_T2 = Input 1 mandatory for the Task 2 of the WP2
				O2_WP3_T1 = Output 2 resulting from Task 1 of WP3

				**): MS Project Task Idenifier:WP: n, Task: m, Output: p, converts into Tn.m.o.p; Example for MS Project Task Output Identifier: WP: 2, Task: 4, Output: 1, converts into 2.4.1 (could also be understood as Output of [Sub-]Task: T2.4.1)

## WP4_IO
			WP4 :	Work Package 4: Validation & Verification Strategy	WP4 Leader: DLR
			Inputs
			Reference(*)	Description	From / (MS Project predecessor)					open Topics	MS Project Identifier
					WP	Task
Input for Task No.?	MS Project Identifier	This Input is part of Deliverable	Input Reference (*)	Description of Input	Producer WP	Producer Task	Comes from what Task? MS-Project Identifier	Preliminary Deadline (latest!)	Status (not started/ in progress/ done)
		D2.3 (will be clarified)	I1_WP4_T1	D2.3: Process definition	2	T2.1, T2.2.	2.2.1, 2.2.2
		D2.4 (will be clarified)	I2_WP4_T1	D2.4: Methods definition	2	T2.2	2.2.2
		D2.9	I3_WP4_T1	D2.9: Set of require-ments for V&V	2	T3.4	2.3.4
		D4.1	I1_WP4_T2	D4.1 V&V Plan & Methodology.	4	1	4.1
		D4.1	I1_WP4_T4	D4.1 V&V Plan & Methodology.	4	1	4.1
		D7.2.1	I2_WP4_T2	D7.2.1 Conclusion on the evaluation of secondary tools and methods and choices	7	2	7.2
		have to be clarified - input from WP 2 or WP 3 concering the SRS?		Preliminary preliminary Prototype Model	WP3/7?	??	3.?, 7.?			SNCF provides input
		have to be clarified - input from WP 2 or WP 3 concering the SRS?	I3_WP4_T2	Preliminary Model, Basline for 1st iteration- used for 1st interim V&V report on the applicability	3	2	3.2			Shold a current model from tool-prototyping activity be taken to ensure V&V applicability?
		have to be clarified - input from WP 2 or WP 3 concering the SRS?	I4_WP4_T2	Preliminary Model, Basline for 2nd iteration - used for report on the prototypical application	3	2	3.2
		D 3.2.3, D3.21	I5_WP4_T2	D3.6: Functional Model (Final Model) - used for final report	3	2	3.2
		D3.3.3 (Date must be clarified with WP 3 leader)	I6_WP4_T2	D3.7: System architecture model Functional Model (Final Model)	3	3	3.3
		D3.2.4	I7_WP4_T2	Functional API - Final - interface to the model at a well defined level	3	2	3.2			Is the API defined within WP2 a detailed specification or on requirements level?
		D4.1	I1_WP4_T1	D4.1 V&V Plan & Methodology.	4	1	4.1
		D 7.2	I2_WP4_T2	Secondary Tools (Tools on V&V)	7	2	7.2
		have to be clarified - input from WP 2 or WP 3 concering the SRS?	I3_WP4_T3	Preliminary Code, Basline for 1st iteration - used for 1st interim V&V report on the applicability	3	4	3.4			Shold a current model from tool-prototyping activity be taken to ensure V&V applicability?
		D3.8	I4_WP4_T3	D3.8: Open Source Code (Preliminary Code, Basline for 2nd iteration) - used for Report on the prototypical application	3	4	4.4
		D3.8	I5_WP4_T3	D3.8: Open Source Code (Final Code) - used for Final report	3	4	4.3
		D3.3.4 (Date must be clarified with WP 3 leader)	I6_WP4_T3	System API - Final - interface to the code at a well defined level	3	3	3.3			Is the API defined within WP2 a detailed specification or on requirements level?
		D2.1	I1_WP4_T4	D2.1 Report on existing methodologies	2	1	2.1
		D2.2	I2_WP4_T4	D2.2 Report on CENELEC standards	2	1	2.1
		D2.3	I3_WP4_T4	D2.3 Process definition	2	2	2.2
		D1.3.1	I4_WP4_T4	D1.3.1 Project Guide on Quality Assurance - Quality Assurance plan is mandatory to establish in Task 4.4 Safety Plan Part 2 "Evidence of quality management"	1	3	1.3	31.03.2013	in Progress
		D2.4	I5_WP4_T4	D2.4: Methods definition - needed to extract system definition (Part 1 Safety Case)and to establish safety plan (Part 3 Safety Case)	2	2	2.2
		D2.5	I6_WP4_T4	D2.5: Description of ETCS using those methodologies (SNCF) - mandatory to extract to establish safety plan (Part 3 Safety Case)	2	T2.2.2.3	2.2.2.3
		D2.6-9	I7_WP4_T4	D2.6-9: Set of Requirements ...- mandatory present a conclusive system definition in part 1 of the Safety Case	2	D2.6-D2.9	2.?
		D7.3.1.1	I8_WP4_T4	D7.3.1.1 Safety Plan (or equivalent)- needed to build a safety evaluation in the Safety Management Plan (Part 3 Safety Case)	7	3	7.3
		D7.3.1.2	I9_WP4_T4	D7.3.1.2 Tools Interoperability Description - basis to provide baseline for a technical safety evaluation (Part 4 Safety Case)	7	3	7.3
		D7.3.2	I10_WP4_T4	D7.3.2 Tool Chain Infrastructure Description - Basis for tool chain system definition and for the Technical Safety evaluation for the software development	7	3	7.3
		D7.3.3	I11_WP4_T4	D7.3.3 Tool Chain Qualification Process Description - Needed to compare against quality assurance plan for the Quality Management report (Part 2 safety case)	7	3	7.3
		D 7.(will be clarified)	I12_WP4_T4	Documentation of the tool characteristics and evaluation of technical risk concerning safety and security based on tool use and tool chain characteristics	7	3	7.3
		D7.3.4	I13_WP4_T4	D7.3.4 Tool chain first release - complete documentation about all tools to evaluate their level of qualification (proof required tool level according to CENELEC) (Part 4 and Part 5 Safety Case)	7	3	7.3
		D 7.(will be clarified)	I14_WP4_T4	Documentation of the ecosystem and evaluation of technical risk concerning safety and security inside the ecosystem	7	4	7.4
		D 7.(will be clarified)	I15_WP4_T4	Documentation of working process (for system specfication model)- concerning tool use and responsible contributors, compliance with quality assurance and safety plan - evaluating independencies to establish Safety Case (Part 5 for software)	3	1	3.1
		D 7.(will be clarified)	I16_WP4_T4	Documentation of working process (for functional model) - concerning tool use and responsible contributors, compliance with quality assurance and safety plan - evaluating independencies to establish Safety Case (Part 5 for software)	3	2	3.2
		D 7.(will be clarified)	I17_WP4_T4	Documentation of working process (for system architecture model) - concerning tool use and responsible contributors, compliance with quality assurance and safety plan - evaluating independencies to establish Safety Case (Part 5 for software)	3	3	3.3
			I18_WP4_T4	Documentation of working process (for Platform independent executable model) - concerning tool use and responsible contributors, compliance with quality assurance and safety plan - evaluating independencies to establish Safety Case (Part 5 for software)	3	4	3.4

				TBD (WP4 + WP1 + WP7 ???)						Should tools/ process + artifacts be assessed and what is needed as an input if so (e.g. digital signature)?

			Ouputs
			Reference(*)	Description	To / (MS Project successor)
					WP	Task
Output from Task No.?	MS Project Identifier	Task Output is part of Deliverable	Output Reference (*)	Description of Output	User WP	User Task	Needed by what Task for MS-Project Identifier	Preliminary delivery time	Status (not started/ in progress/ done)
	4.1.1	D4.1	O1_WP4_T1	D4.1 V&V Plan & Methodology.	4	2 & 3	4.2, 4.3
				D4.1a: preliminaryEvaluation criteria on V&V	7, 2	7.1
	4.2.2	D4.2.1	O2_WP4_T2	D4.2.1 1st interim V&V report on the applicability of the V&V approach to the formal abstract model.	3	6	3.6
	4.3.1	D4.2.2	O1_WP4_T3	D4.2.2 1st interim V&V report on the applicability of the V&V approach to the implementation / code.	3	8	3.8
	4.2.2	D4.3.1	O2_WP4_T2	D4.3.1 Report on the prototypical application of the V&V tool chain and processes / - for the formal model & formal abstract model	3	6	3.6
	4.3.2	D4.3.2	O2_WP4_T3	D4.3.2 Report on the prototypical application of the V&V tool chain and processes / - for the implementation / code of the formal model	3	6	3.6
	4.4.1	D4.3.3	O1_WP4_T4	D4.3.3 Report on the prototypical application of the V&V tool chain and processes / - Safety case for the tool chain and the processes	3	8	3.8
	4.2.2	D4.4	O2_WP4_T2	D4.4 Final report and conclusions of the whole WP4 (Part V&V Report on the Model)	4	4	4.4
	4.3.3	D4.4	O3_WP4_T3	D4.4 Final report and conclusions of the whole WP4 (Part V&V Report on the code/ Implementation)	4	4	4.4
	4.4.4	D4.4	O4_WP4_T4	D4.4 Final report and conclusions of the whole WP4 (Part Safety Case and completion of Document)	Foundation?
				D 4.4a preliminary Evaluation criteria on safety	7,2	7.1
	4.4.5	D4.5	O5_WP4_T4	D4.5 Quality recommendation to prepare the Assessment	Assessor					Do 24.09.15

			(*) :	[I;O] index_WP number_T[ask] number
			Examples :	I1_WP2_T2 = Input 1 mandatory for the Task 2 of the WP2
				O2_WP3_T1 = Output 2 resulting from Task 1 of WP3

				**): MS Project Task Idenifier:WP: n, Task: m, Output: p, converts into Tn.m.o.p; Example for MS Project Task Output Identifier: WP: 2, Task: 4, Output: 1, converts into 2.4.1 (could also be understood as Output of [Sub-]Task: T2.4.1)

## WP5_IO
			WP6 :	Work Package 6: Dissemination, Exploitation and Standardization	WP6 Leader: TWT GmbH
			Inputs
			Reference(*)	Description	From / (MS Project predecessor)
					WP	Task
Input for Task No.?	MS Project Identifier	This Input is part of Deliverable	Input Reference (*)	Description of Input	Producer WP	Producer Task	Comes from what Task? MS-Project Identifier	Preliminary Deadline (latest!)	Status (not started/ in progress/ done)

			Ouputs
			Reference(*)	Description	To / (MS Project successor)
					WP	Task
Output from Task No.?	MS Project Identifier	Task Output is part of Deliverable	Output Reference (*)	Description of Output	User WP	User Task	Needed by what Task for MS-Project Identifier	Preliminary delivery time	Status (not started/ in progress/ done)

			(*) :	[I;O] index_WP number_T[ask] number
			Examples :	I1_WP2_T2_1 = Input 1 mandatory for the Task 2 of the WP2
				O2_WP3_T1_2 = Output 2 resulting from Task 1 of WP3

				**): MS Project Task Idenifier:WP: n, Task: m, Output: p, converts into Tn.m.o.p; Example for MS Project Task Output Identifier: WP: 2, Task: 4, Output: 1, converts into 2.4.1 (could also be understood as Output of [Sub-]Task: T2.4.1)

## WP6_IO
			WP6 :	Work Package 6: Dissemination, Exploitation and Standardization	WP6 Leader: TWT GmbH
			Inputs
			Reference(*)	Description	From / (MS Project predecessor)
					WP	Task
Input for Task No.?	MS Project Identifier	This Input is part of Deliverable	Input Reference (*)	Description of Input	Producer WP	Producer Task	Comes from what Task? MS-Project Identifier	Preliminary Deadline (latest!)	Status (not started/ in progress/ done)

			Ouputs
			Reference(*)	Description	To / (MS Project successor)
					WP	Task
Output from Task No.?	MS Project Identifier	Task Output is part of Deliverable	Output Reference (*)	Description of Output	User WP	User Task	Needed by what Task for MS-Project Identifier	Preliminary delivery time	Status (not started/ in progress/ done)

			(*) :	[I;O] index_WP number_T[ask] number
			Examples :	I1_WP2_T2_1 = Input 1 mandatory for the Task 2 of the WP2
				O2_WP3_T1_2 = Output 2 resulting from Task 1 of WP3

				**): MS Project Task Idenifier:WP: n, Task: m, Output: p, converts into Tn.m.o.p; Example for MS Project Task Output Identifier: WP: 2, Task: 4, Output: 1, converts into 2.4.1 (could also be understood as Output of [Sub-]Task: T2.4.1)