openETCS Workshop
openETCS itea2 Review
WP7 – Toolchain Development
supported by:
openETCS@ITEA2 Project
Michael Jastram
Munich, June 12th, 2014

---
The Big Picture
RM Tool
WP2
Requirements
WP7
Toolchain
WP3
Modeling
Modeling Tools
Safety Analysis Tools
Requirements
WP4
V&V
V&V Tools
Feedback
Model Transformation
Tools
WP5
Demonstrator
Code Generation Tools
Image courtesy of -Marcus- / FreeDigitalPhotos.net
Traceability
Integration
Qualification

---
An Integrated Tool Chain
Source: https://github.com/openETCS/requirements/tree/master/D2.6-9
Image courtesy of graur codrin / FreeDigitalPhotos.net

---
Workpackage Structure
WP7 Toolchain
Michael Jastram / Formal Mind
T7.1 Primary Toolchain
Marielle Petit-Doche / Systerel
T7.2 Secondary Toolchain
Marielle Petit-Doche / Systerel
T7.3 Toolchain Development
Cécile Braunstein / University Bremen
T7.4 Ecosystem
Jonas Helming / EclipseSource
Image courtesy of Vichaya Kiatying-Angsulee / FreeDigitalPhotos.net

---
Timeline
OpenETCS
Kick-Off
First benchmark started
Decision on Primary Tooling
Second Release of tool chain
12 benchmarks underway
WP7: Tooling
Decision on Secondary Tooling
WP3: Modeling
First release of tool chain
Split of WP3
2013
2012
2014
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Development Infrastructure
WP7 DoW complete
 WP2 deliverables complete
Architecture
Decomposition & Distribution of work
1st Scrum Sprint
First preliminary WP2 deliverables
Image courtesy of -Marcus- / FreeDigitalPhotos.net

---
2014 – 2015: Regular releases
Project
ends
2015
20
14
Q3
Q4
Q2
Q3
Q4
Q1
Q2
Today (Toolsprint 13)
milestone releases
2 weeks
Image courtesy of Vichaya Kiatying-Angsulee / FreeDigitalPhotos.net
Source: https://en.wikipedia.org/wiki/File:Scrum_process.svg

---
Status Deliverables
1. D7.1: Evaluation Primary Tools: Delivered
2. D7.2: Evaluation Secondary Tools: Delivered
3. D7.4: First Toolchain Release: Delivered
5. D7.3: Qualification Process: Delayed
  1. Draft available since January 2014
  2. Lack of resources prompted to focus on too chain development process
  3. Lack of feedback from the partners
  4. Lack of expert on tool qualification

---
Collaborations
https://github.com/openETCS/toolchain/wiki/Collaborations
Delegates maintain contact with these projects:
- Polarsys (aka OPEES, aka Topcased)
- shift2rail
- Crystal
- SAFE
- SafeCap
- VeTeSS
- EATS FP7 project
- OpenRBC
- Amalthea
- OpenCOSS
Image courtesy of hywards Kiatying-Angsulee / FreeDigitalPhotos.net

---
openETCS:
open Extended Tool Construction Set

---
Feature Overview
https://github.com/openETCS/toolchain/wiki/Feature%20Overview
Requirements
Safety
EN
50128
Subset
26, 1-6
Traceability
System Modeling
V&V
Configuration
Management
Subset
26, 7-8

---
Product Backlog (uses gitHub infrastructure)

---
Demo
Image courtesy of Stuart Miles / FreeDigitalPhotos.net

---
Escalation: WP Objectives endangered
1. Transition from Phase 1 (Analysis) to Phase 2 (Tool Development) unveiled problems:
  1. Technology not as mature as expected
  2. Important Skills are missing
  3. Resources are Fragmented
Image courtesy of David Castillo Dominici / FreeDigitalPhotos.net

---
Escalation: Technology Maturity
“You get what you pay for”
- Topcased/PolarSys much less mature than expected
      - Papyrus is the only usable PolarSys Component
      - CEA 100% fixing Papyrus issue (unspecific to openETCS)
      - No mature Traceability solution available
- ProR/RMF (Requirements) needs significant work
      - Many “standard” functions still missing
      - Performance issues
- Minor issues eating up resources
      - Java 7 in enterprise environment is tricky
      - Providing cross-platform support
      - Building and maintaining infrastructure (update sites, build server, documentation infrastructure, etc.)
Image courtesy of David Castillo Dominici / FreeDigitalPhotos.net

---
Escalation: Resource Situation
At first glance, not too bad:
60% active (incl. Papyrus)
20% research
20% overhead, exhausted and inactivity
Image courtesy of David Castillo Dominici / FreeDigitalPhotos.net

---
Escalation: Who can Develop Software?
Reason to worry:
Only 5% of Eclipse development active (excluding Papyrus)
30% of active participants learning
Image courtesy of David Castillo Dominici / FreeDigitalPhotos.net

---
Escalation: Fragmentation
Image courtesy of David Castillo Dominici / FreeDigitalPhotos.net

---
Escalation: Possible Solutions
1. Problem: Technology Maturity
  1. Use of proprietary technology
2. Problem: Missing Skills
  1. Training
  2. Get new partners with the right skills by picking up French funds
  3. Spend funds to hire experts
3. Problem: Fragmentation
  1. Aggregate resources: Few partners with many resources, not many partners with few.
  2. Build a core team: Find at least 3 team members (better 4) with the right skills that work full time on WP7.
Image courtesy of David Castillo Dominici / FreeDigitalPhotos.net

---
Thanks to the team
Task Leader 7.1 and 7.2
Marielle Petit-Doche / Systerel
Task Leader 7.3
Cécile Braunstein / University of Bremen
Task Leader 7.4
Jonas Helming / Eclipse Source
Thanks
to the openETCS WP7 Team
Image courtesy of sritangphoto / FreeDigitalPhotos.net