## Sheet1
	Week 1					Week2
	Monday	Tuesday	Wednesday	Thursday	Friday	Monday	Tuesday	Wednesday	Thursday	Friday
WP7 Pariticipants	Choose task from the backlog	Scrum telco		Scrum Telco			Scrum Telco		Scrum Telco
	Assign task to the current sprint	Clean the issues tracker of the current sprint		Discussion on a specific topic			Discussion on a specific topic		Clean-up issue tracker: roll all unresolved issue into the backlog
	Fill the activity log	Decide on Topic priority with stakeholder		Grooming issues			Grooming issues
Task leader	Create a new milestone	Add releases goals in the milestone main issue								Close milestone
	Create the Milestone main issue containing the checklist	Complete Scrum session planning								Announce new release
	Increment the Milestone qualifier									Updates release links
Assignees										Trigger new Build
										Test installer/updater